## Tracker
ID | Pillar | Offer service line | Activity | Output / deliverable | Owner | Support | Phase | Start | Due | Priority | Definition of Done | Depends On
FT-01 | Operational Setup | Business Setup | Register the company and open a business bank account | Certificate of incorporation and bank account confirmation | Awa | David | Phase 1 | 2026-10-12 | 2026-10-23 | high | The company is legally registered and the account can send and receive payments
FT-02 | Legal & Compliance | Business Setup | Draft and sign the founding team agreement | Signed founders' agreement | Awa | David | Phase 1 | 2026-10-12 | 2026-10-30 | high | Every founder has signed the equity, roles and vesting agreement | FT-01
FT-03 | Operational Setup | Business Setup | Set up financial tracking and accounting | Configured accounting workspace and chart of accounts | Nadia | David | Phase 1 | 2026-10-19 | 2026-11-06 | medium | Every planned expense can be recorded, categorised and reported | FT-01
FT-04 | Product & Tech | Platform Setup | Stand up the cloud environment and deployment pipeline | Deployed staging environment with automated builds | Kofi |  | Phase 1 | 2026-10-19 | 2026-11-13 | high | A commit deploys to staging automatically and the app is reachable
FT-05 | Legal & Compliance | Business Setup | Establish the data-protection and farmer-consent policy | Signed-off privacy policy and consent form | Awa | David | Phase 1 | 2026-10-26 | 2026-11-13 | high | The policy is published and consent is captured in the onboarding flow | FT-04
PL-01 | Product & Tech | Pilot Programme | Install soil-moisture sensors on the pilot farms | Sensors deployed and reporting readings | Kofi | Sarah | Phase 2 | 2026-11-16 | 2026-11-27 | high | Sensor readings are visible in the platform for every pilot plot | FT-04
PL-02 | Product & Tech | Pilot Programme | Build the farmer onboarding mobile flow | Onboarding screens in the mobile app | Kofi |  | Phase 2 | 2026-11-16 | 2026-12-04 | high | A farmer can register a plot and see it on the map | FT-04
PL-03 | Field Operations | Pilot Programme | Recruit and contract ten pilot farmers | Signed pilot agreements for ten farms | Sarah | Awa | Phase 2 | 2026-11-16 | 2026-12-11 | high | Ten farmers have signed and completed onboarding | FT-05
PL-04 | Field Operations | Pilot Programme | Train the farmers to use the platform | Training session and quick-start guide | Sarah |  | Phase 2 | 2026-12-01 | 2026-12-18 | medium | Every pilot farmer has completed a hands-on training session | PL-02/PL-03
PL-05 | Product & Tech | Pilot Programme | Connect the irrigation advisory engine to live sensor data | Working irrigation recommendations | Kofi |  | Phase 2 | 2026-12-07 | 2026-12-24 | high | The platform issues an irrigation recommendation from live data | PL-01
PL-06 | Field Operations | Pilot Programme | Run the first full crop cycle with the pilots | Crop-cycle field log | Sarah | Kofi | Phase 2 | 2026-12-28 | 2027-02-26 | high | One complete crop cycle is monitored end to end with data captured | PL-04/PL-05
PV-01 | Data & Analytics | Impact Measurement | Define the yield and water-saving metrics | Metrics definition document | Nadia | Sarah | Phase 2 | 2026-12-14 | 2027-01-08 | high | Baseline and target metrics are agreed for every plot | PL-05
PV-02 | Data & Analytics | Impact Measurement | Analyse the pilot results against the baseline | Pilot impact report | Nadia |  | Phase 3 | 2027-03-01 | 2027-03-19 | high | The report quantifies water saved and the change in yield | PL-06/PV-01
PV-03 | Product & Tech | Platform Setup | Harden the platform from pilot feedback | Prioritised backlog with critical defects fixed | Kofi |  | Phase 3 | 2027-03-01 | 2027-03-26 | medium | All critical pilot defects have been resolved | PL-06
PV-04 | Product & Tech | Platform Setup | Add offline data capture for low-connectivity farms | Offline sync feature | Kofi |  | Phase 3 | 2027-03-15 | 2027-04-09 | high | Data captured offline syncs once connectivity returns | PL-06
PV-05 | Data & Analytics | Impact Measurement | Package the validated impact case study | Farmer testimonial and one-page case study | Awa | Sarah | Phase 3 | 2027-03-22 | 2027-04-09 | high | A publishable case study with farmer quotes and numbers | PV-02
GT-01 | Marketing | Commercial | Define the pricing and subscription model | Pricing sheet and pilot offer | Awa | Sarah | Phase 4 | 2027-04-12 | 2027-04-30 | high | Pricing has been validated with three farmers and documented | PV-05
GT-02 | Marketing | Commercial | Build the website and brand assets | Live landing page and brand kit | Sarah |  | Phase 4 | 2027-04-12 | 2027-05-07 | medium | The landing page is live with a working sign-up
GT-03 | Marketing | Commercial | Produce the sales deck and one-pager | Sales deck and printable one-pager | Sarah | Awa | Phase 4 | 2027-04-19 | 2027-05-14 | medium | The deck is ready to present to a partner or investor | GT-01
GT-04 | Sales | Commercial | Sign the first three paying cooperatives | Signed service contracts | Awa | Sarah | Phase 4 | 2027-05-03 | 2027-06-11 | high | Three cooperatives have signed and paid the first invoice | GT-01/GT-03
GT-05 | Sales | Commercial | Set up billing and payment collection | Working billing flow | Nadia |  | Phase 4 | 2027-05-03 | 2027-05-28 | medium | A customer can be invoiced and pay online | GT-01
GT-06 | Operations | Commercial | Define and staff the customer-support process | Support playbook and ticketing setup | Sarah |  | Phase 4 | 2027-05-17 | 2027-06-04 | low | Support requests are logged and answered within the agreed time | GT-04
IR-01 | Finance | Investor Readiness | Build the financial model and unit economics | Financial model workbook | Nadia | Awa | Phase 5 | 2027-06-14 | 2027-07-09 | high | A three-year model with validated unit economics | GT-04
IR-02 | Finance | Investor Readiness | Prepare the investor data room | Investor data room | Awa | Nadia | Phase 5 | 2027-06-21 | 2027-07-16 | high | All key documents are indexed and shareable | IR-01
IR-03 | Fundraising | Investor Readiness | Create the investor pitch deck | Final pitch deck | Awa | Sarah | Phase 5 | 2027-06-21 | 2027-07-16 | high | The deck covers problem, solution, traction, market and the ask | IR-01/GT-04
IR-04 | Fundraising | Investor Readiness | Build the target-investor list and outreach plan | Investor outreach pipeline | Awa | David | Phase 5 | 2027-07-05 | 2027-07-30 | medium | Thirty qualified investors with contact details and a sequenced plan | IR-02
IR-05 | Fundraising | Investor Readiness | Run the raise and close the first commitment | Signed term sheet or first commitment | Awa | David | Phase 5 | 2027-08-02 | 2027-09-24 | high | At least one committed investment for the round | IR-03/IR-04

## Milestones
Checkpoint | Date | Milestone | What must be true
M1 | 2026-11-13 | Foundation & Compliance Setup | FT-01/FT-02/FT-03/FT-04/FT-05 complete — the company can operate, deploy and process farmer data legally
M2 | 2027-02-26 | Farmer Pilot Deployment | PL-01/PL-02/PL-03/PL-04/PL-05/PL-06 complete — ten pilot farms running a full crop cycle on the platform
M3 | 2027-04-09 | Product & Data Validation | PV-01/PV-02/PV-03/PV-04/PV-05 complete — impact measured and a publishable case study ready
M4 | 2027-06-11 | Go-To-Market & First Revenue | GT-01/GT-02/GT-03/GT-04/GT-05/GT-06 complete — three paying cooperatives signed and supported
M5 | 2027-09-24 | Investment Readiness | IR-01/IR-02/IR-03/IR-04/IR-05 complete — the round is open with a first commitment